13	Procurement Strategy and Implementation Plan	278

13.1	Introduction	278

13.1.1	General	278

13.1.2	Definitions	279

13.1.3	Legislation	280

13.1.4	Procurement Steps	281

13.2	Procurement Strategy	284

13.2.1	Implementation of Investments, Phase-II	284

13.2.1.1	Summary of Procurement Strategy	287

13.2.1.2	Proposed Procurement and Implementation Plan	288

13.2.1.3	Implementation	290

13.2.1.4	Implementation Plan	292

13.2.2	Operation of Implemented Investments in Phase-II	293

13.2.2.1	Considerations on waste service delivery	293

13.2.2.2	Identification and analysis of service providers	298

13.2.2.3	Transitional Operational Arrangements	301

13.2.2.4	The existing contracts in the Arges County – zones 1, 2, and 8	302

13.2.2.5	Modification of existing contracts	303

13.2.2.6	Patrimony	304

13.2.2.7	Right of administration	304

13.2.2.8	Conclusions and recommendations	305

# Procurement Strategy and Implementation Plan

## Introduction

The present document has been prepared in the frame of Technical Assistance (TA) for Project Preparation in the Waste sector EuropeAid/122694/D/SER/RO. This TA provides for the provision of waste management infrastructure and related requirements for Arges County in Romania. This document has therefore been prepared to detail the implementation and procurement arrangements that should accompany the specific ERDF investments that are referred in this document in Arges County.

### General

The requirement for a Procurement Strategy and implementation Plan is required when the decision to purchase works, equipment or services has been made, thus the right strategy has to be followed in order to efficient the process and reach the targets.

Procurement planning is used as an opportunity to evaluate/review the entire procurement process so that sound judgements and decision making will facilitate the success of the overall project. The Project Implementation Plan and Procurement Plan described herein are designed to facilitate the implementation and procurement of works, equipment and services for the Project: TA for Project preparation in the Waste Sector – Romania, specific for Arges County, Phase-II.

The Master Plan as well as the Feasibility Study covers the period 2009 – 2039 and detail proposals for the integrated solid waste management of Phase-II in Arges County, including temporal storage, collection, sorting, transfer, land filling with associated treatments and the closure and rehabilitation of existing landfills. All the proposed measures have to comply with EC legislation within the agreed transitional periods. The present section deals in detail with the procurement and implementation phase for the priority investment measures of the project in Phase-II. The components for which the procurement strategy and implementation plan shall be adopted are defined by the findings and conclusions of the Feasibility Study.

The overall items considered under the project are:

- Collection System for Residual Waste and Packaging Waste;

- Extension of an existing sorting plant;

- Treatment of Biodegradable Waste (windrow composting);

- Logistics (Transfer and Transport);

- Closure of non-compliant disposal sites;

- Relocation and remediation of an urban disposal site;

- New Cell for final disposal.

The priority investment measures from the above operational system as developed under the project have been defined as:

- Procurement of Containers;

- Construction of Platforms;

- Construction of 2 civic amenity areas;

- Extension of a Sorting Plant;

- Procurement of Individual Composters;

- Construction of  2 Transfer Stations;

- Closure of one existing urban disposal site;

- Relocation and remediation of a urban disposal site;

- Construction of Cell-2.

On of the main features of the IWMP-Arges County in its Phase-II is the fact that the implementation of the project is financed from public funds with support of the Romanian Government and the European Union. Hence, the procurement must strictly follow the Romanian national procurement law. All legal requirements concerning quality and composition of tender documents, concerning realisation of all steps of the tendering procedure, concerning recognition of the legal periods for tendering, evaluation and award and finally concerning the formal approach to all tendering and award activities have to be truly respected. The implementation of the project requires the tendering and award of works contracts, consulting service contracts, supply contracts and operation service contracts.

### Definitions

According to the Government Emergency Ordinance (OUG 34/2006) that regulates the procedures for awarding the public procurement contracts, public works concession contracts, services concession contracts and the legal remedies related to these, the following definitions are applied:

Procurement. Procurement is the process of obtaining supplies, services and construction works; a process that encompasses the full life cycle of the asset or service contract. The ‘life cycle’ is the period from the initial definition of the business need through to the end of the useful life of the asset or service contract. Procurement has a far wider scope than ‘purchasing’, ‘buying’ or ‘commissioning’. It is about securing services and products that best meet the needs of users, the final beneficiaries and national bodies in its widest sense.

Procurement Plan. The procurement plan depicts in detail, which steps have to be undertaken in order to realise the different contract awards and which time schedule has to be followed. On this occasion the different periods for tender announcement, tendering, tender evaluation up to the contract award are truly considered.

Procurement Strategy.  The procurement strategy shows which types of contracts are to be tendered and awarded and which grouping of contracts is seen reasonable. At the same time an overview about the different legal contract principles and foundations is given with the procurement strategy.

Works Contract. Works contracts are those contracts which are tendered and awarded for the purpose to procure construction performances irrespective which type of construction activities is concerned.

For the purpose of the implementation of the present project it is foreseen that also limited supply activities will be tendered and awarded under the service contracts if the relevant supplies are strongly related to the subject of works (e.g. landfill equipment to be tendered together with the works contract for landfill construction).

Consulting Service Contracts. For the purpose of the present document a difference is made between “consulting services” and “operation services”. In this context consulting service contracts are considered to be addressed to pure consulting activities such as supervision of works and supply contracts, technical assistance to PIU and / or execution of public awareness campaigns.

Supply Contracts. The purpose of supply contracts is the delivery of goods such as containers for residue waste and packaging waste collection. Supply contracts at the occasion of the present document apply only, where the supplies are not strictly related to construction investments.

Operation Service Contracts. That type of contracts refers to the award of system operation activities such as waste collection, waste transport, operation of system facilities (transfer stations, landfill, sorting plant, etc.).

Implementation Plan. The implementation plan is the sequence of activities that describe the order, in which every activity will be carried out. The sequence obey the logic of the addressed process, as well as the needs for logic of the envisaged project investments for each works, equipment and services are detailed in attached bar chart. The purchase of equipment is linked with the progress of the works and the technical assistance services are connected to both implementing of the works and equipment purchase.

### Legislation

The Government Emergency Ordinance no. 34/2006 regarding the award of public procurement contracts, public works concession contracts and services concession contracts, approved by Law 337/2006, amended and supplemented by Law 128/2007 and G.E.O. 94/2007 (see Annex 13.1-1).

This Ordinance establishes that contracting authority has to disclose within the documentation annexed to the procurement agreement all the criteria, regulations and other necessary information required to ensure that each bidder has received complete information as related to the acquisition procedure to be followed. This documentation is supposed to focus particularly on those technical facts that must be explicitly defined within the tender book regarding the qualitative, technical and performance factors of the tender.

The contracting authority must publish through the ESPP (Electronic System for Procurement Procedures), a contract notification setting out its needs and requirements, which it must define in the notice and/or in a related descriptive document. The Official Gazette may continue to be used for this purpose along with two new specific methods of informing potential contractors: a public acquisition electronic system to be used inside Romania started in January 1, 2007, and the Official Journal of the European Union for European wide use (also commencing with January 1, 2007). Until December 31, 2006, the contracting authority had continue to publish the contract notice within the Official Gazette and must use the two new methods only in cases where it considers it to be appropriate.

It has to be noticed that the Romanian procurement law (in compliance with the relevant European regulations) defined some thresholds of contract values, which require publication in the OJ (Official Journal of EU). The consequences are mainly related to the minimum periods for announcement, tendering evaluation and award procedure. These thresholds are defined with:

- 125.000,- EUR / contract for services

- 400.000,- EUR / contract for supplies

- 5.000.000,- EUR / contract of works

The procedures for awarding the public procurement contract are defined as follows:

Open procedure. Defined as the procedure to which any interested economic operator has the right to submit tenders.

Restricted Procedure. Defined as the procedure to which any economic operator has the right to submit his candidature, but where only selected candidates by the contracting authority, are invited to submit tender.

Competitive Dialogue. Defined as the procedure to which any economic operator has the right to submit his candidature for a complex contract and which the contracting authority conducts a dialogue with the admitted candidates. The dialogue is necessary to assist the authority in identifying and defining one or more suitable solutions that are able to respond to its needs and on the basis of which the selected candidates will elaborate the final tender

Negotiation. Defined as the procedure by which the contracting authority carries out consultations with the selected candidates and negotiates the contractual clauses, including the price, with one or more of those. The negotiation can be:

- negotiation with prior publication of a contract notice;

- negotiation without publication of a contract notice.

Request for Tenders. Defined as the simplified procedure by which the contracting authority requests for tenders from several economic operators.

### Procurement Steps

The main Procurement stages include four key steps:

- Tender announcement period (procurement notice / forecast notice)

- Tendering period:

- Application phase (where applicable, but not foreseen here)

- Invitation to tender

- Preparation and submission of tender proposals by the bidders (including clarifications, site visits, etc.)

- Contract award period:

- Evaluation of tender proposals (including conduction of interviews and clarifications)

- Contract award (award letter, contract)

- Contract execution:

- Execution of contractual obligations by the successful bidder(s)

- Take over of works, services and supplies

- Defects notification and remediation (during warranty period)

- Final take over

At the same time, the Romanian procurement law sets different legal periods for the different procurement activities (open & restricted tenders), i.e.,

  - Open Tenders

- Publication of Procurement Notice (PN) – not mandatory. To be published only in case the Contracting Authority intends to reduce the mandatory period for the submission of tenders or if the value of the contract is higher than EUR 750,000 (for services and goods) or EUR 5,000,000 (for works).

- Publication of the tender notice (TN).

  - If the value of the contract exceeds 125,000 euro for services / 400,000 euro for supplies / 5,000,000 euro for works – mandatory publication in the OJ (Official Journal of EU) - regular period for submission of tenders (after publication of TN): 52 days

    - In case a FN was published and the period between the publication of FN and TN is less than 12 months and at least of 52 days – period for submission of tenders – at least 36 days

    - In case the TN is published in OJ– reduction of the period with 7 days.

    - In case the tender documents are published in SEAP, reduction of the period with additional 5 days.

  - If the value of the contracts is below the above thresholds:

    - regular period for submission of tenders (after publication of TN): 20 days

    - In case the tender documents are published in SEAP, reduction of the period with additional 5 days.

- Evaluation. As per procurement law, the period between the opening of tenders and selection of the winning offer shall be not more than 20 days. Exceptionally, with justification, extension to not more than 40 days is possible. Letters to all tenderers should be sent within 3 days from the selection of the winner.

- Signature of the contract. The Contracting Authority is allowed to sign the contract only:

  - 11 days after having informed the tenderers (in case the value of the contract exceeds the above threshold)

  - 6 days after having informed the tenderers (for contracts not exceeding the thresholds)

The above deadlines are not mandatory in case of one tender only. The winning company is notified in writing and invited for the signature of the contract.

- Commencement of the contract. As specified in the contract conditions, no conditions imposed.

  - Restricted Tenders

- Publication of Procurement Notice (PN) – not mandatory.

- Publication of the tender notice (TN).

  - If the value of the contract exceeds 125,000 euro for services / 400,000 euro for supplies / 5,000,000 euro for works – mandatory publication in the OJ (Official Journal of EU)

- regular period for submission of tenders (after publication of TN): 37 days; in justified cases (urgency), not less than 15 days

- In case the TN is published in OJ– reduction of the period with 7 days; in the 2nd scenario – reduction with 5 days

  - If the value of the contracts is below the above thresholds:

    - regular period for submission of tenders (after publication of TN): 10 days

- Invitation to Tender

      - If the value of the contract exceeds 125,000 euro for services / 400,000 euro for supplies / 5,000,000 euro for works – mandatory publication in the OJ (Official Journal of EU) - regular period for submission of tenders (after publication of TN): 40 days

        - In case a FN was published and the period between the publication of FN and TN is less than 12 months and at least of 52 days – period for submission of tenders – at least 36 days and in exceptional cases not less than 22 days

        - In case the tender documents are published in SEAP, reduction of the period with additional 5 days.

        - In justified cases (urgency), not less than 10 days

      - If the value of the contracts is below the above thresholds:

        - regular period for submission of tenders (after publication of TN): 15 days

        - In case the tender documents are published in SEAP, reduction of the period with additional 5 days.

- Evaluation

As per procurement law, the evaluation period – shall be not more than 20 days. Exceptionally, with justification, extension to not more than 40 days is possible. Letters to all tenderers should be sent within 3 days from the selection of the winner.

- Signature of the Contract

The CA is only allowed to sign the contract:

- 11 days after having informed the tenderers – in case the value of the contract exceeds the

- above thresholds 6 days after having informed the tenderers (for contracts not exceeding the thresholds)

The above deadlines are not mandatory in case of one tender only. Winning company is notified in writing and invited for the signature of the contract.

- Commencement of the Contract

As specified in the contract conditions, no conditions imposed.

  - Contract Management and Supervision

During this phase, the Beneficiary through the Project Implementation Unit (PIU) with the Consultant Supervisors, will manage and supervise the contracts by working closely with the contractors, suppliers and consultants to ensure that contract requirements are met. The purpose of the Contract Management and supervision Step is to ensure that the contractors, suppliers and consultants and the works, equipment, products or services delivered comply with the contract requirements. The Contract management and Supervision will perform the following functions:

- Interpret specifications;

- Ensure that quality of the works, equipment, products or services is maintained;

- Direct change management;

- Administrative changes,

- Budgetary changes,

- Contract modifications (if necessary) and associated change order (get proper approvals),

- Manage smaller, incidental contracts for work associated with the project.

- Resolve contract disputes;

  - Part of the work may be accepted, or

  - All of the work may be rejected, or

  - Work may be accepted with provisions for corrections in the future.

- Completion of the project;

- Ensure that all project requirements are complete per contract,

- Terminate the contract;

  - Default of contract; Contractor fails to perform any provision of the contract including:

  - Failure to deliver by scheduled date,

  - Failure to make progress (endangers performance of the contract).

  - Termination for Convenience (e.g., project cancelled)

  - Manage contract risk associated with the project.

## Procurement Strategy

The procurement strategy for Phase-II of IWMP-Arges is divided into two main parts:

      - Procurement strategy for the implementation stage of the investments for Phase-II

      - procurement strategy for operation contracts of implemented investments for Phase-II

### Implementation of Investments, Phase-II

Tenders shall be grouped under consideration to award similar activities to similar bidders on one hand and under the intention to limit the number of contractors, service providers, suppliers and operators as much as reasonable on the other hand. The first criterion assures that no bidder tenders for activities out of his competence and the second criterion assures a minimum on administrative and coordination efforts for the Contracting Authority.

It is anticipated and shown with a long range of experiences that large scale contracts will have lower unit prices (e.g. reduction of overhead share, secured capacity use, etc.). It makes therefore extremely good sense not to split the project into too small portions but to have a reasonable grouping of contracts according to above criteria.

For the dates given in the Procurement Plan apply the following assumptions:

- The Application is approved by the Beneficiary and the MoEF before 15th of February 2011;

- The Application is approved by the European Commission (EC) before 30th of February 2011.

          - Consulting Service Contracts

The grouping of consulting service contracts will depends on the nature of consulting service on one hand, and on avoidance of conflicts of interest on the other. Thus the technical assistance (general consultancy) to the PIU and the beneficiary has to be strictly separated from other consultancy activities.

Even here it is anticipated that large scale contracts provide lower unit costs in comparison with small scale contracts, thus the different activities shall not be split further (e.g. per component or however) but be awarded each on the county scale. However, there are some consulting services that owing their nature and due to the acquired experience of PIU, in implementing Phase-I (ISPA investments), require to be split and form in total 3 services contracts.

Service Contract #1 Technical Assistance for the Management and Supervision Support of Integrated Waste Management in Arges County, Phase-II.  This service contract will include the following:

  - Detail design of 1 closure, the IWM Facilities (2 TS including 2 composting plants and 2 civic amenity areas) and the waste storage and collection system of Phase-II of IWMP-Arges

  - Preparation of Tender Documents for work and supply contracts

  - supervision of all works and supply contracts as concerned by the “project”

  - Technical checking of design and approvals

  - technical assistance to PIU and beneficiary

  - conduction of public awareness campaigns

  - Tariff study and PPP study and selection

In this regard it is recommended to use the services of a professional marketing and / or advertising company for the conduction of public awareness campaigns.

Service Contract #2 Technical Assistance for technical revision of design and approvals of Integrated Waste Management in Arges County, Phase-II.  This service contract will include basically the revision and corresponding approvals for all designs of the IWM Facilities (2 TS including 2 composting plants and 2 civic amenity areas) and the waste storage and collection system of Phase-II of IWMP-Arges.

Service Contract #3 Technical Assistance for independent evaluation of Tender Procedures of Integrated Waste Management in Arges County, Phase-II.  This service contract will include basically the independent evaluation of all work contracts of Integrated Waste Management in Arges County, Phase-II

    - Works Contracts

Principally works contracts will be split according to the special type of works for:

- Cell-2 construction, landfill closure, relocation and remediation of urban dumpsites (which is similar nature of works). The main works are as following:

      - first construction period: 1st half of 2011 for closure of Curtea de Arges disposal site by interim cover system and IWMF

      - second construction period by end of 2013:

- Cell-2 Construction at Albota Landfill and

- final cover system at Curtea de Arges disposal site after the main settlements are ceased

In respect of the first construction session and according to the obtained experienced with the implementation of Phase-I of the IWMP-Arges, the main works for the construction of the Integrated Waste Management Facilities (IWMF) in Curtea de Arges, Costesti and Albota, as well as operation areas, composting areas, utility and traffic infrastructures, administration buildings, extension of sorting plant, etc. – will be tendered acc. to construction type of contract (equivalent to FIDIC Red Book). This approach has been appointed as the one offering the major advantages for the beneficiary.

Owing the nature of required works and facilities, the works Contracts will be:

      - Works Contract  # 1

- Construction of:

  - Interim cover system at Curtea de Arges disposal site,

- Construction of the IWMF at Curtea de Arges and Costesti, for utility and traffic infrastructures, administration buildings, open side covers, civic amenity areas, weighbridges, tyre wash facilities, site operation roads. Additionally the construction of collection platforms, for waste collection, belongs to this part, as works are related.

These will be realised by construction type of contract (equivalent to FIDIC Red book)

- Construction of Cell-2 Construction at Albota Landfill and final cover system at Curtea de Arges disposal site after the main settlements are ceased (end of 2013). Owing the resource saving, these two works have been included in the same contract, rather than making a new one, where new tender is necessary.

      - Works Contract # 2

- Relocation and Remediation of:

  - Relocation & remediation of Costesti disposal site to Albota landfill,

      - Works Contract # 3

        - Construction of sorting plant extension  for recyclables at Albota facilities that will be realised according to design build type of contract (FIDIC Yellow Book)

        - Improvement of composting plants at Campulung and Albota (FIDIC Yellow Book)

In this regard it is foreseen to tender and award 3 different contracts. This is not unusual and it provides numerous advantages, which are briefly summarised below:

- Similar performances will be provided by one contractor only who takes full responsibility of the coordination of all works and supplies needed for the fulfilment of the contractual scope and obligations.

- That minimises the risk of claims made by the contractors of different type, in case of obstructions for site access, caused by other contractors etc. and it minimises even the coordination efforts of beneficiary and consultant significantly.

- The responsibility for defects on similar works can not be argued by the contractor, since he was the only one providing those performances on the site.

- Beneficiary and consultant have not much counterparts for all organisational matters who also takes the responsibility of unlimited information transfer to sub-contractors and partner companies working under his patronage on the site.

- The financial and accounting issues are simplified with 3 an not 5 contracts, also in view of bid bonds, performance guarantees, interim payment requests, quantity survey etc.

- The PIU in Arges has already the experience from Phase-I, which ensures a easier and smoother implementation for Phase-II

    - Supply Contracts

The supply contracts will mainly address the required goods, equipment and machinery for temporal storage and collection services of the project, and others from the IWMF.

Owing the difficulty to group supply contracts, since different suppliers (meaning either manufacturers or dealers) are limited in the provision of goods, equipment and machinery, it is foreseen to allocate supplies, which are strongly connected to separate investment measures (e.g. storage & collection systems, transfer stations, composting plants, civic amenity areas, etc.) to the relevant works contracts.

The contracts have therefore to be separated according to the nature of supplies as follows:

- supply of waste containers and bins for collection (bins of 120 L and 1,1 m³ containers according to EN 840-2/5/6)

- supply of machinery for IWMF (waste compactors, wheel loaders, street sweepers, HHW collection trucks, weighbridges, shredders, etc.), closed landfill monitoring equipment, containers for the civic amenity areas, auxiliary equipment for the sorting plant (containers, forklift, wheel loader) and furniture, computer equipment etc. for the administration buildings will be realised according to supply contract conditions.

#### Summary of Procurement Strategy

The procurement strategy for the implementation of the IWMP in Arges County in Phase-II, can be summarised as follows,

| Contract | Type | Comments |
| --- | --- | --- |
| Contract # 1: “Technical Assistance for the Management and Supervision Support of Integrated Waste Management in Arges County, Phase-II” |  |  |
| Including: - Detail design of 1 closure - TD for works contract - supervision of works and supply contracts - technical assistance to PIU and beneficiary - conduction of public awareness campaigns - Tariff study - PPP study - Selection of operators | Services IRT (updated GEO no. 34/2006) |  |
| Contract # 2: “Technical Assistance for technical checking of design and approvals of Integrated Waste Management in Arges County, Phase-II” |  |  |
| a. Technical checking of designs and approvals | Services IRT (updated GEO no. 34/2006) |  |
| Contract # 3: “Technical Assistance for independent evaluation of Integrated Waste Management in Arges County, Phase-II” |  |  |
| a. Independent evaluation of tenders for work contracts | Services IRT (updated GEO no. 34/2006) |  |
| Contract # 4: “Closure of landfill Curtea de Arges, Construction of Cell-2 and Construction of IWMF” |  |  |
| a. Construction of Interim cover system at Curtea de Arges disposal site, | Works ICB (updated GEO no. 34/2006 +FIDIC RED) |  |
| b. IWMF of Curtea de Arges and Costesti, i.e., b.1 transfer station of Curtea de Arges and Costesti b.2 Composting plant of Curtea de Arges & Costesti b.3 Related utility and traffic infrastructures, administration buildings, civic amenity areas, open side covers, weighbridges, tyre wash facilities, site operation roads, etc. b.4 Collection platforms for waste collection |  |  |
| c. Construction of c.1Final cover system of Curtea de Arges site c.2 Cell-2 at Albota landfill | Works ICB (updated GEO no. 34/2006 +FIDIC RED) |  |
| Contract # 5: “Relocation/remediation of Costesti disposal site ” |  |  |
| a. Relocation and remediation of: a.1 Costesti disposal site into Albota landfill | Works ICB (updated GEO no. 34/2006 +FIDIC YELLOW) |  |
| Contract # 6: “Extension of sorting plant at Albota WMC and improvement of CP at Campulung & Albota” |  |  |
| - Construction of Sorting plant extension for recyclables, with a capacity of 20.000 tons/year at Albota IWMC - Improvement of composting plants at Campulung and Albota | Works ICB (updated GEO no. 34/2006 +FIDIC YELLOW) | Considered as best contracted under FIDIC Yellow Book. |
| Contract # 7: “Supply of goods, equipment and machinery for integrated waste management system ” |  |  |
| LOT 1: Supply of goods, machinery and equipment for IWMF, i.e. - 2 transfer stations - 2 composting plants - 2 civic amenity areas | Supply ICB (updated GEO no. 34/2006) | The delivery time has to be close related with the delivery of finished works at TS, CP and Civic amenity areas |
| LOT 2: Supply of: - Waste containers of 1.1 m3 capacity (according to European Norm EN 840-2/5/6) - Waste bins 0f 120 L capacity (according to European Norm EN 840-2/5/6) - Individual composters | Supply ICB (updated GEO no. 34/2006) | Consideration should be given to the provision of collection bins by the collection operators. |

Note. GEO: Government Emergency Ordinance no. 34/2006 Romania; FIDIC: International Federation of Consulting Engineers; ICB: International Competitive Bid; TD: Tender Documentation.

#### Proposed Procurement and Implementation Plan

    - Legal Frame

- Tender dossiers will be developed according to the latest Romanian laws regarding public procurement. The latest legal acts are:

- Emergency Governmental Ordinance no. 19/2009 (amendment of Government Emergency Ordinance No 34/2006), regarding awarding of public procurement contracts, contracts of concession of public works and contracts for concession of services. Published in Official Gazette No. 156/12.03.2008;

- Emergency Governmental Ordinance no. 94/2007 (amendment of Government Emergency Ordinance No 34/2006), regarding awarding of public procurement contracts, contracts of concession of public works and contracts for concession of services. Published in Official Gazette No. 676/04.10.2007;

- Emergency Governmental Ordinance no. 143/2008 (amendment of Government Emergency Ordinance No 34/2006), regarding awarding of public procurement contracts, contracts of concession of public works and contracts for concession of services. Published in Official Gazette No. 805/02.12.2008;

- Order no. 155/2006 for approval of the Guidelines for awarding of public procurement contracts;

- Emergency Governmental Ordinance no. 228/2008 (amendment of Government Emergency Ordinance No 34/2006), regarding awarding of public procurement contracts, contracts of concession of public works and contracts for concession of services. Published in Official Gazette No. 3/05.01.2009;

- Law no. 337, June 17 of 2006 for approval of Emergency Governmental Ordinance no. 34/2006 regarding awarding of public procurement contracts, contracts for concession of public works and contracts for concession of services;

- Decision no. 925, July 19 of 2006 for approval of the methodological norms of provisions related to award of public procurements contracts, contracts for concession of public works and contracts for concession of services.

    - Assumptions

As mention above, the main assumptions to take into account for the Procurement Plan are related to the Applications approval dates, i.e.

- The Application is approved by the Beneficiary and the MoEF before 15th of March 2011;

- There will be availability of funds to finance the project

The Environmental permit is already issued in 1st of April 2005 and renovated on 31.07.2009.

    - Risks and suggested measures

- A smooth and continuous co-operation of all stakeholders and full support in all administrative and approval matters by PIU and REPA is assumed.

  - Risk: delayed approval of Implementation Program may lead to a delay in the elaboration of bid documents.

  - Suggested solution: Preparation of the reports and documents in close and continuous co-operation between Technical Assistance (TA) Consultants and PIU, this also by providing pre-versions or parts for approval.

- The smooth co-operation of the local authorities in obtaining the necessary permits and authorizations is assumed.

  - Risk: Project implementation is delayed.

  - Suggested solution: Participation of all involved local authorities in the Project preparation including all permits to be further assessed by the TA Consultant.

- No delays in the Prequalification and Tender processes.

  - Risk: Delays in bid process will lead to a delay of the overall Project implementation schedule.

  - Suggested solution: TA Consultant shall provide a high quality support to PIU to avoid any delays of Project implementation and Tender Process, e.g. by a stringent and transparent communication process.

- An acceptable Tender is not received or the Contract(s) is (are) not signed before or within a reasonable period of the scheduled commencement dates agreed in the Services Contract, for any reason.

  - Risk: Extension of the overall Project implementation schedule.

  - Suggested solution: The TA Consultant shall provide sufficient support during the whole bid process to the Client and in responding queries and clarifications for Tenders, in order to minimize this risk

Should these situations arise, the TA Consultant would respond positively in assisting the PIU to seek and find a solution acceptable to all parties leading to satisfactory completion of the Project.

#### Implementation

The table below undertakes to summarise the different contracts to be tendered for implementation and operation of the integrated integrated waste management system (please note that the contractual periods are provisionally only):

| Contract | Components / Duration | Conditions | Procedure | Estimated Value (€ without VAT) |
| --- | --- | --- | --- | --- |
| Contract # 1 |  |  |  |  |
| Technical Assistance for the Management and Supervision Support of Integrated Waste Management in Arges County, Phase-II | Period (05/2011 – 12/2015). - Detail design of 1 site closure and IWMS, Phase-II - Tender documentation of work contracts - supervision of works and supply contracts - technical assistance to PIU and beneficiary - public awareness campaign Tariff study - PPP study - Selection of operators | Services IRT (updated GEO no. 34/2006) | Open public (international) | 2.470.000 |
| Contract # 2 |  |  |  |  |
| Technical Assistance for technical revision of design and approvals of Integrated Waste Management in Arges County, Phase-II | Period (03/2011 – 12/2013). - Technical revision of final designs - Tramit and obtaining of approvals for WM facilities | Services IRT (updated GEO no. 34/2006) | Open public (international) | 70.000 |
| Contract # 3 |  |  |  |  |
| Technical Assistance for independent evaluation of Tender Procedures of Integrated Waste Management in Arges County, Phase-II | Period (03/2011 – 08/2012). - Independent evaluation of tender for works contracts | Services IRT (updated GEO no. 34/2006) | Open public (international) | 60.000 |
| Contract # 4 |  |  |  |  |
| Closure of landfill Curtea de Arges, Construction of Cell-2 and Construction of IWMF | Period (05/2011 - 08/2012). a. Construction of Interim cover system at Curtea de Arges disposal site, inc. gas landfill extraction system. | FIDIC Red Book | Open public (international) | 1.682.603 |
|  | Period (05/2011 - 11/2012). b. Construction of the IWMF of Curtea de Arges and Costesti, i.e., b.1 transfer station of Curtea de Arges and Costesti b.2 Composting plant of Curtea de Arges & Costesti b.3 Related utility and traffic infrastructures, administration buildings, civic amenity areas, weighbridges, tyre wash facilities, site operation roads, etc. b.4 Collection platforms for waste collection | FIDIC Red Book |  | 2.402.937 |
|  | Period (07/2013 - 12/2013). c. Construction of c.1 Final cover system of Curtea de Arges site c.2 Cell-2 at Albota landfill | FIDIC Red Book |  | 4.794.910 |
| Contract # 5 |  |  |  |  |
| Relocation/remediation of Costesti disposal site | Period (08/2011 – 08/2012). a. Relocation and remediation of: a.1 Costesti disposal site into Albota landfill | FIDIC Yellow Book | Open public (international) | 1.303.428 |
| Contract # 6 |  |  |  |  |
| Extension of sorting plant at Albota WMC and improvement of CP at Campulung & Albota | Period (03/2011 - 05/2011). - Construction of Sorting plant extension for recyclables, with a capacity of 20.000 tons/year at Albota IWMC - Improvement of composting plants at Campulung and Albota | FIDIC Yellow Book | Open public (international) | 420.000 |
| Contract # 7 |  |  |  |  |
| Supply of goods, equipment and machinery for integrated waste management system | LOT 1 (07/2012 - 10/2012): Supply of goods, machinery and equipment for IWMF, i.e. - 2 transfer stations - 2 composting plants - 2 civic amenity areas | Supply ICB (updated GEO no. 34/2006) | Open public (international) | 1.795.755 |
|  | LOT 2 (08/2011 - 10/2011): Supply of: - Waste containers of 1.1 m3 capacity (according to European Norm EN 840-2/5/6) - Waste bins 0f 120 L capacity (according to European Norm EN 840-2/5/6)) - Individual composters | Supply ICB (updated GEO no. 34/2006) |  | 1695.223 |

It has to be mentioned that according to the Romanian legislation and standards for works contracts a 12 months defects notification period (DNP) follows upon the finalisation of the physical construction works. That has to be added to the construction periods as stated in the table below. Thus the works contracts will be considered finalised after DNP only.

#### Implementation Plan

According to the Romanian Procurement Process, it can be truly anticipated that the tendering period for each of the contracts to be awarded will last about 3 months. Since complaints and contests made by the bidders to the proposed awards on one hand but also unexpected delays within the application and approval phase of the projects on the other hand can not be comprehensively calculated in the time scheduling, all dates for launching the tender procedures, starting the contract executions finalising the contracts (specifically works contracts).  For this reason the last dates have to be considered as provisional dates and might need some further adjustments during the following project periods and phases.

Anyway, procurement plan and implementation schedule depend on several factors, out of which the most significant are:

- legal periods (according to the procurement regulations on one hand but according to approval and permission requirements on the other hand) and technical periods (according to the time need for document preparation) to be followed in the tendering procedure

- legally and technically required precedence of implementation (e.g.: the Cell-1 has to be completely depleted, before the new Cell-2 starts operations).

- technically required construction periods (e.g.: different time needs for construction and equipment for different system components, thus the entire system  shall be finished and ready for work at more or less the same time, since otherwise defects of construction works might not be notified.)

- capacity of the beneficiary to deal with numerous tendering activities at the same time

Therefore the procurement plan is designed to handle the above factors with due diligence and for the maximum benefit with lowest risks in implementation.

It is assumed that tender process of the Contract 1 for Technical Assistance for the Management and Supervision Support of Integrated Waste Management in Arges County, Phase-II will start by end March 2011 and the tender process of the rest of Contracts will start by first quarter of 2011 and will last 3 months for all contracts to be tendered. That refers to the following contracts:

- Service Contract 2: Technical revision of designs and approvals

- Service Contract 3: Independent evaluators for work contracts

- Works contract 4: Closure  of landfill Curtea de Arges, Construction of Cell-2 and Construction of IWMF

- Works contract 5: Relocation/remediation of Costesti disposal site

- Works contract 6: Extension of sorting plant at Albota WMC and improvement of CP at Campulung & Albota

- Supply contract 7: Supply of goods, equipment and machinery for IWMF and supply of containers and bins for waste collection and individual compost devices

The following schedule summarises the sequence and duration of procurement and execution of the different contracts as stated in above table.

IWMF. Integrated Waste Management Facilities that include related utility and traffic infrastructures, administration buildings, civic amenity areas, weighbridges, tyre wash facilities and site operation roads

### Operation of Implemented Investments in Phase-II

This section deals with the analysis of the various options to arrange for operation of project facilities, a review of transitional arrangements and recommendations with regard to Assets Management.

#### Considerations on waste service delivery

After the investment phases will be finished, the management of these facilities will be delegated through management delegation contracts to operators, by means of public tenders.

Contracts will need to be concluded with operators for the management of the activities composing the sanitation services including waste collection, transfer, long distance transportation, treatment, processing and disposal.

Several waste management operational services will be provided under the new waste management system, such as:

- Management of the WMC, including sorting and composting activities, and disposal of waste at the landfill.

- Management of the (3) transfer stations.

- Long-hauling of waste to the WMC in Albota.

- Collection of municipal waste in the various localities and transportation to the transfer stations, or directly to the landfill in Albota.

The first question is how many different contractual frameworks are required to implement the proposed waste management system. The following options are suggested:

- Four framework contracts, each of them covering one activity (one for collection, another one for management of the transfer stations, a third for long-hauling of waste between TS and landfill, and the last one for operating the landfills).

- One framework contract covering all the activities (collection, management of the transfer stations, long-hauling of waste between TS and landfill, and operating the landfills).

- Specific contractual frameworks, partially covering the services.

The key advantages and disadvantages of these approaches are identified in the following table:

|  | Advantages | Disadvantages |
| --- | --- | --- |
| Option 1: Four contractual frameworks, one for each of the four services. | - Contract monitoring and performance precisely linked to individual contracts. - Maximizes opportunity for local companies to compete. - Specific contracts mean performing specialized functions. | - Leaves no room for achieving economies of scale, which could lead to high operational costs. - Standardization of services over the county as a whole more difficult - Interesting only for SMEs, which could have underdeveloped operational capacity. - The tendering and monitoring requirements are high. |
| Option 2: One contractual framework for all services. | - Minimizes tendering and monitoring requirements. - Lower costs than other options, if economy of scale is achieved. - Attracts big and well developed companies (some of them could be from the current service providers) | - The scope of contract could be too wide for any competitor. - Small chance for a competitive bidding process. - Places high demands for monitoring of the level of service on Contracting Authorities. |
| Option 3: Specific contractual frameworks. | - Allows operational services to be grouped according to required functions and capacities. - A certain level of economies of scale could be achieved. - Increases the competitiveness in the bidding process - More opportunities for different companies. - The tendering and monitoring processes are more cost-effective. - Provide more solutions to diminish the risks. | - The preparation of tenders is more difficult, since appropriate contract packages should be determined. - The tendering and monitoring requirements are reasonable. |

Based on the table above, it is concluded that there are serious disadvantages to setup four different contractual frameworks, one for each of the four activities (Option 1). The same conclusion is applicable for Option 2 (one contractual framework for all activities). It is therefore recommended to have specific contractual frameworks (Option 3), and the possibilities which could be considered in this situation are analysed in the following paragraphs.

Consequently, the remaining question is how to group the services, between specific contractual frameworks?

To analyse the possible responses to this question we have to bear in mind two important aspects:

- who is the owner of the assets , and

- what kind of financial arrangements will be settled in order to obtain a sustainable waste management system.

The following table presents the legal aspects in respect with this issues.

| ACTIVITIES | INFRASTRUCTURE |  | RELEVANT LOCAL PUBLIC AUTHORITY | MANAGEMENT DELEGATION CONTRACTS WITH THE OPERATORS | SIGNATORY OF THE CONTRACT |
| --- | --- | --- | --- | --- | --- |
|  | Assets | Owner |  |  |  |
| Waste collection (including the separate collection) | Containers, vehicles for the collection and transport of waste | Either the localities, or the operator, or the County (for vehicles and equipment financed by the Project) | The Local Councils that put together the assets and the activities within IDA, and the County Council if it owns a part of infrastructure’s assets | There shall be one delegation contract for each area served by a transfer station. | IDA in the name and on behalf of its concerned members The Local Councils in the designated areas, as counter-signing the contracts, |
| Waste transport to the transfer stations | Vehicles for the transport of waste | Either the localities, or the operator, or the County (for vehicles financed by the Project) | The Local Councils that put together the assets and the activities within IDA, and the County Council if it owns a part of infrastructure’s assets | The transport activity shall be delegated by the same contract, to the same operator, as for collection. | IDA in the name and on behalf of its concerned members The Local Councils in the designated areas, as counter-signing the contracts, |
| Management of the transfer stations | Transfer stations | County | County Council | The management of the transfer stations activity shall be delegated -either by the same delegation contract as for the collection and transport to the transfer stations, and to the same operator -or by the same delegation contract as for management of the activities of management of the WMC, and to the same operator. | - IDA if the first option is chosen - the County if the second option is chosen |
| The transport from the transfer stations to the landfill | Vehicles for the transport of waste | The County (if the assets are financed by the Project), or the operator | County Council | The activity of transport from the transfer stations to the integrated waste management centre may be delegated as follows : - either by the same delegation contract as for the collection, transport to the transfer stations, and management of the transfer stations to the same operator, - or to the operator that manage the WMC, by the same contract | - IDA if the first option is chosen - the County if the second option is chosen |
| The management of the waste management centre (WMC) | The landfill, the sorting centre and all other assets related to the WMC | County Council | County Council | The management of the activities of management of the integrated waste management centre shall be delegated by a single contract, to an unique operator for all the Project’s area, which shall be different from the operators to which are granted the contracts regarding the collection and waste transport to the transfer stations. | County Council |

Taking into consideration the above mentioned aspects, what it could be concluded is that the WMC should be handle by one operator, the collection of waste should be operated by several operators, and there are some alternatives for the management of the transfer stations and long-hauling the waste to the WMC.

Consequently, in respect with the scope of contracts, we are going to analyse three possible alternatives:

- The operator of the WMC will manage the transfer stations and long-hauling of waste to the WMC.

- The collection operators will manage the transfer stations (which are in their operational areas) and the long-hauling of waste to the WMC will be managed by the WMC operator.

- Three sets of operators:

- Collection operators, which are managing the collection and transportation of waste to the transfer stations, or to the WMC (which is closer).

- Transfer operator(s), which are managing the transfer stations and long-hauling of waste to the landfill.

- The WMC operator, who is managing the landfill operations

Option 1: The Collection operators will manage the transfer stations, while the hauling of waste is managed by the WMC operator.

Collection ICI

Collection HH

Management Transfer Station(s)

-composting

-green points

Management of WMC

-sorting

-composting

- green point

Scope of Collection Contracts

Scope of WMC Operator Contract

Disposal at

the landfill

Long-haul to WMC

weighing bridge

weighing bridge

Figure 13.1 Option 1- proposed scope of contracts

Advantages

- Assure the correlation between the collection activity and the transfer stations activity, in terms of schedule, waste management, etc.

- The management of the transfer station is less costly, compare with the other options.

- Standardization of long-haul equipment (large containers) is easier to achieve, since it belongs to one operator.

- The operational area for the WMC operator is concentrated around the landfill, which means the management will be less costly, compare with the other options..

Disadvantages

- The financial burden for the transfer of waste (investment and operational costs) is unequally divided among the payers within the county.

- The owner of the assets is the CC, and the tender for collection of waste is done by IDA, situation which could increase the risks, if it is not properly managed.

- The delegation contracts with the collection operators are more difficult to be managed.

Option 2: WMC operator is managing the Transfer Stations and long-hauling of waste

Collection ICI

Collection HH

Manag.

Transfer Station(s)

- composting

- green points

Management of WMC

-sorting

-composting

- green point

Scope of Collection Contracts

Scope of WMC Operator Contract

Disposal at

the landfill

Hauling to WMC

weighing bridge

weighing bridge

Figure 13.2 Option 2- proposed scope of contracts

Advantages

- Potential legal conflicts between ownership of assets (CC) and concession of collection services by IDA are being avoided.

- The collection operators have only one activity (waste collection).

- Standardization of long-haul equipment (large containers) is easier to achieve, since it belongs to one operator.

- The financial burden for the transfer of waste (investment and operational costs) is equally divided among the payers within the county.

Disadvantages

- An identification system needs to be installed in order to monitor the quantities arriving from waste collection areas.

- High managerial cost in managing the transfer stations, due to their location in the county.

- Increased risk of waste dumping due to a possible lack of collection between the activity of the collection operators and the transfer stations open schedule.

- The delegation contract for WMC operation is more difficult to be managed.

Option 3: Three sets of operators

Collection ICI

Collection HH

Manag.

Transfer Station(s)

-composting

-green points

Management of WMC

-sorting

-composting

- green point

weighing bridge

Scope of Collection Contracts

Scope of WMC Operator Contract

Disposal at

the landfill

Hauling to WMC

Scope of Transfer Contract (s)

weighing bridge

Figure 13.3 Option 3- proposed scope of contracts

Advantages

- The operational areas are distinct, through the separation between collection, transfer, and treatment of waste.

- Standardization of transfer equipment (especially large containers) is easier to achieve.

Disadvantages

- More operators could mean higher taxation.

- The financial burden for the transfer of waste (investment and operational costs) is unequally divided among the payers within the county, since in three operational area the waste is disposed directly to the landfill.

- Increased possibility for legal disputes between the operators.

- The number of delegation contracts is higher, which means high contract management costs.

In conclusion, based on the above analysis and after several discussions with the Beneficiaries, the most suitable option for service delivery in Arges County is option 1: the collection operators will manage the transfer stations, while the long-haul of waste is managed by the WMC operator.

Consequently, the delegation contracts should be signed under three different types of contractual frameworks, which will lead to a number of 7 operators for the whole system:

- First contractual framework is for WMC operations, which include management of the WMC and long-hauling the waste from the transfer stations to the WMC.

- The second contractual framework is for the waste collection and management of transfer station (with composting and green points facilities), for the operators in the zones 1&2 (Curtea de Arges), 3&4 (Câmpulung), and 8 (Costeşti).

- The third contractual framework is again for waste collection, for the operators which will transport the waste directly to the WMC (zones 6-North, 6-South, and 5&7).

#### Identification and analysis of service providers

There are a number of options available for the delivery of the waste management services described in the previous section. In this analysis four options are analyzed as follows:

- Department within public authority without separate legal status;

- Organisation subordinated to local public authority with separate legal status;

- PPP with private investments (BOO, BOT, Concession Contracts)

- PPP with public ownership (service, management, lease Contracts)

The choice of a service delivery model should ensure:

Operational autonomy

- This requires an institutional separation of functions between the administration and the operation of service delivery.  Failure to ensure this separation has high potential to result in service inefficiency and ineffectiveness over time as a result of conflict between administrative and operational priorities.

Capacity to perform

- The new regionalized waste management system will require higher levels of performance capacity than have been previously required.

Cost competitiveness

- There should be initial assurance that the operator is cost-competitive within the sector and that mechanisms are in place to ensure that operators remain cost competitive.

Monitoring effectiveness

- Effective waste management systems include effective monitoring mechanisms that hold the service operator accountable for its performance, and which link payment and/or contracting to satisfactory performance.

Previousla were identified the key strengths and weaknesses of the three service delivery models with respect to these criteria. As identified, the public sector approaches are not evaluated as favourably as the private sector models. This is because public sector models,

- May experience significant political involvement in operational matters, and this serves to undermine the capacity of professional staff to properly manage the waste management system

- Do not offer incentives to maximize performance at either an institutional or individual level, with the result that capacities may be weaker in public sector delivery models.

- Are not subject to the same level of competitive pressure as the private sector, and therefore do not have similarly effective internal checks and balances to ensure competitiveness.

- Are not effective at monitoring and evaluating own performance, with the result that service quality suffers over time.

County Council or IDA

Option 2.1.

PPP with private investments (BOT, BOO, Concessions)

Option 1.1.

Department within local public administration (i.e. Local/County Council)

Option 2.2.

PPP with public investments

Option 2:

Delegate management (PPP options)

Option 1:

Direct management

Option  1.2.

Public company, subordinated to local public authorities (i.e. Local/County Council)

Figure 13.4 Options for services providers

It is therefore recommended that service delivery is undertaken through Option 2.1 or Option 2.2 identified in Figure 5.4. Key considerations in evaluating these options include:

- Availability of capital resources . Option 2.1 (PPP with private investments) is attractive where public capital resources are not available, or are not competitive, with private capital resources.  Where this is the case, private capital resources can be accessed to invest in required waste management facilities, and the private sector investor recovers this cost through charging for operations.

Option 2.2 (PPP with public investment) is attractive where public capital resources are available for capital investment at rates that are more favorable than similar resources from the private sector or where private capital investments are unlikely to occur due to high risks or lack of interest.  Under this option, lower waste management costs can be achieved than are possible under Option 2.1 to the extent that the cost of capital is lower under this option.

- Management flexibility . Option 2.1 (BOT, BOO or Concession Contracts) requires the signing of a long term contract in order for capital investments to be fully amortized.  This ties a public entity to the same service delivery entity over the period of the contract.  The public entity therefore has no opportunity to change the service delivery entity if service delivery is unsatisfactory, and the service delivery entity has little incentive to respond to the evolving concerns of the public sector contracting body.

Under Option 2.2 (Services, Management or Lease Contracts), capital costs for waste treatment/disposal/transfer facilities are met through the public sector, so that private sector amortization over extended periods of time is not an issue.  Accordingly, service or management delegation contracts can be negotiated over shorter periods of time (5 – 10 years is common).  This provides a private sector contractor with greater incentive to perform well (because it will want to be awarded the contract for future waste management services) and at the same time provides the contracting authority with the opportunity to retain a new contractor in the future if better terms of service performance are available.

It is therefore recommended that service delivery for all required waste management services will be undertaken through Option 2.2 (Services, Management or Lease type of Contracts). The local authorities will deliver waste management services through “delegated management” contracts. If the delivery of waste management services will be performed using facilities and/or equipment owned by the public authorities, management delegation contracts will take the form of lease contracts that will specify (among other things) performance criteria and maintenance schedule(s) that the contractor will be responsible to maintain as a condition of payment and which will be monitored by the PIU together with the IDA.

| PPP Type | Main Features | Application | Strengths | Weaknesses |
| --- | --- | --- | --- | --- |
| DBFO | Contract with a private party to design, build, operate and finance a facility for defined period, after which the facility reverts to the public sector. The facility is operated by the private sector for the contract period and it recovers costs through public subvention. Key driver is the utilization of private finance and transfer of design, construction & operating risk. Variant forms involve different combinations of the principle responsibilities. | Suited to projects that involve a significant operating content. Particularly suited to roads, water and waste projects. | Attracts private sector finance; Attracts debt finance discipline; Delivers more predictable and consistent cost profile; Greater potential for accelerated construction programme; and Increased risk transfer provides greater incentive for private sector contractor to adopt a whole life costing approach to design. | Possible conflict between planning and environmental considerations. Contracts can be more complex and tendering process can take longer than for BOT. Contract management and performance monitoring systems required. Cost of re-entering the business if operator proves unsatisfactory. Funding guarantees may be required. Change management system required. |
| Concession | As for DBFO except private party recovers costs from user charges. Key driver is the Polluter Pays Principle and utilising private finance and transferring design, construction and operating risk. | Suited to projects that provide an opportunity for the introduction of user charging. Particularly suited to roads, water (non-domestic) and waste projects. | As for DBFO plus: Facilitates implementation of the Polluter Pays Principle; and Increases level of demand risk transfer and encourages generation of third party revenue. | As for DBFO plus: May not be politically acceptable Requires effective management of alternatives / substitutes, e.g. alternative transport routes; alternative waste disposal options). |
| Service Concession | Private sector partner becomes operator of publicly financed and owned facilities and covers costs by a fee agreement with the public authority. | Suited for a broad range of municipal services including water, wastewater, solid waste removal, road maintenance, parks maintenance/ landscape maintenance, arenas and other recreation facilities, sewer and storm sewer systems. | Potential service quality and efficiency improvements, cost savings, flexibility in structuring contracts, ownership vests with local government. | Collective agreements may not permit contracting out, costs to re-enter service if contractor defaults, reduced owner control and ability to respond to changing public demands. |

#### Transitional Operational Arrangements

Concerning transitional operational arrangements, in Arges County the situation is already settle for the zones 3,4,5,6, and 7. New operators will be selected in 2010 and their contractual framework is established in respect with the requirements of the new IWM system.

Therefore, in this report we will focus on the current and future situation for the zones 1,2 and 8, where the new IWM will bring two transfer stations (in Curtea de Arges and Costesti), and two waste collection areas (one for zones 1&2, and the other for zone 8).

- Legal issues

The previous Government Ordinance no 87/2001 (abolished and replaced by Law no 101/2006 currently in force) instituted the principle according to which local authorities can delegate waste management services by public tender, on the basis of ‘management delegation contracts’ or ‘concession contracts’, having due regard to the framework regulation for the delegation of the management of the sanitation services and the framework management delegation contract, to operators having a license issued by ANRSC. However, local public authorities had the right to grant directly such contracts to companies totally owned by them.

Government Ordinance no 87/2001 provided that, in order to finance the necessary investments for the development and the modernization of the waste management infrastructure, local authorities can contract internal/external loans or they can concede the service to private investors for limited periods, as follows:

- maximum 8 years – for pre-collection, collection and transport of waste

- maximum 20 years – for the establishment and the management of the ecological landfills, including the selection and recycling of waste.

The Framework regulation and the Framework contract were approved only in 2004 by Government Decision no 346/2004. The Framework regulation provided that:

- each local authority must draw up and approve its own strategies and local organisation and functioning regulations of its sanitation services;

- in order to conclude a management delegation contract, the local public authorities were obliged to draw up and approve an opportunity study,  which included the elements provided by Law no 219/1999, i.e. a description of the service and/or assets to be conceded, the reasons of environmental, social, financial and economic nature justifying the granting of the concession, the necessary investments for modernizations and/or extension of the services, the minimum level of services, the estimated duration of the concession etc.;

- the delegation of the management of the sanitation services must be performed transparently, exclusively by public tender and only to economic agents certified by ANRSC

Initially, Law no. 101/2006 contained no provisions regarding the granting of the delegation contracts. The Government’s Emergency Ordinance no. 92/2007, which amended Law no 101/2006, introduced a new article which stipulates that the granting procedures and the legal regime of the delegation contracts are those provided by Government’s Emergency Ordinance no 34/2006 regarding the granting of the public procurement contracts, of the public works concession contracts and of the public services concession contracts (which abolished the above mentioned Law no. 219/1999).

According to Government’s Emergency Ordinance no. 34/2006:

- local authorities have the obligation to grant concession contracts through public tender or competitive dialogue procedures;

- in order to conclude the concession contracts, the local public authorities are obliged to draw up and approve a justification study (quite similar to the opportunity study provided by the Framework regulation).

#### The existing contracts in the Arges County – zones 1, 2, and 8

Zone-1 - Curtea de Argeş city

The urban area in Zone 1 is represented by Curtea de Argeş city. The storage of municipal solid waste in the city is carried out at the source of generation, in households and commercial establishments, and by means of 34 collection platforms

The collection of solid waste in Curtea de Argeş is carried out mainly by two operators, one is private and the second is public. These operators are:

- S.C. TRANSARG CAG '98 - collection and transport of the domestic solid waste;

- Communal administration public service subordinated to the City Hall– collection and transport of street waste.

Rural area of Zone 1 - Curtea de Argeş

The collected data about the current situation of temporal storage and waste collection, in the rural area of Zone 1, state that temporal storage of household waste is carry out mostly in containers owned by householders. The type of container used for this purpose varies with each householder, as well as the capacity. In many cases the used containers are improvised containers, which do not comply with sanitary requirements.

The storage of solid waste in improvised containers takes place in the most of rural areas of Zone 1, except in the communes Valea Iasului and Valea Danului. These communes have contracted the collection service of solid waste with S.C. TRANSARG CAG '98. Hence, the company has distributed 179 and 140 bins (120 – 240 litres) to individual households to carry out the temporal storage of solid waste.

In general, no specialized collection service exists in the rural area of Zone 1-Curtea de Argeş. As mentioned before, this situation is different only in the communes Valea Iasului, Valea Danului and Arefu, where S.C. TRANSARG CAG '98 performs the collection service of solid waste. This company includes, in its collections routes of Curtea de Argeş city, the communities abovementioned.

Zone 2 - Domnesti

The Zone 2-Domnesti consists entirely of rural areas, including the communes and their villages. The storage of solid waste in the most of the Zone is carried out by householders with several kinds of containers, owned by householders. However, in the commune Domnesti the waste collection service is contracted with a private company, S.C. Financiar Urban S.R.L. Pitesti.

Zone 8 - Costesti city

The urban area in the entire Zone 8 is represented by Costesti city. The temporal storage of solid waste in this city is carried out at the source of generation, in households and commercial entities. The devices used for this purpose are containers owned by households and commercial units, many of these are not specialized waste containers, but rather improvised containers used for this purpose.

Regarding the collection and transport of solid waste in the urban area of Zone 8-Costesti, this is carried out with two trucks owned by the public service from communal administration, subordinated to the City Hall. This entity carries out the specialized service of collection and transport of household and street waste.

Rural area of Zone 8-Costesti

The collected data about the current situation of temporal storage and waste collection, in the rural area of Zone 8, state that temporal storage of household waste is carry out mostly in containers owned by householders. The type of container used for this purpose varies with each householder, as well as the capacity. In many cases the used devices are improvised containers, which do not comply with sanitary requirements.

In some communes (like Bârla, Buzoieşti), the councils have organized certain endowments and personal to carry out the waste collection service, mainly for households. In the other communes, with no collection service, the waste is individually transported, from temporal storage to final disposal, by householders and commercial owners.

It is important to point out that for the most of those communes, with communal service for waste collection, the transport of the amount of collected waste is towards controlled disposal sites in urban areas. In this case the main disposal site is located in Costesti. For those communes without waste collection service, the collected data shows that the solid waste is transported by generators to non-compliant disposal sites.

The lack of organized collection service for solid waste in the rural area of Zone 8-Costesti favours the development of the uncontrolled waste deposits in rural areas, where there is any collection service.

Other data about the operators

Besides the main activity of the operators that carry out the collection and transport service, they also carry out also the activities of sanitation, disinfection and pest control, collection activities of plastic type PET recipients, and also activities of collecting paper and cardboards.

The Local Public Domain Administrations carry out all the activities from the area of the public services, namely, water - sewer – heat – parks’ administration, repairing and maintaining streets.

Table 5.4: Current contractual situation

| Signatory parties | Contract no.&date | Coverage area | Duration | Termination of contract |
| --- | --- | --- | --- | --- |
| Curtea de Arges Municipality – S.C. TRANSARG CAG '98 | No. 2 / 02.08.1999 | Curtea de Arges municipal area. | 10 years + prolonged with 5 years in 2009 | LCO nr. 81 / 30.06.2009 Art. 2: “The contract will be terminated when the components of the integrated management system will be functional (within each operational zones).” |
| Domeşti Local Council – S.C. Financiar Urban S.R.L. Pitesti. | No. 2014 / 25.08.2005 | Domneşti area | undetermined | Chapter XII, art.17: - agreement of the parties; - the LCs’ unilateral decision, with 30 days notice, only after the operator is paid for performed services. - the Operator, after 30 days since the contract was suspended (for unpaid services). - if the operator is in a restructuring process. |

For more information please consult Annex E - Current contracts in the zones 1,2 and 8.

#### Modification of existing contracts

The administrative-territorial units are subject to the rights and to the obligations resulted from the contracts regarding the administration of the goods belonging to private and public property from which they are part, and also the results from the relationship with other individuals or juridical entities, in accordance with the law.

The received information from the local beneficiary is complete, so we extracted a few conclusions:

- There are more “service contracts” than there are concession/delegation contracts;

- They have few clauses;

- They do not make any reference to the status and to the level of the services approved by the local council;

- The contracts do not have performance and evaluation indicators of the sanitation services;

- The contracts have clauses regarding the possibility that the local councils to annul the existent contracts closed with the operators, once the new system of solid waste will constructed and authorized.

The clauses regarding the foreseen cease provisioned by the existent contracts are:

- The written accord of the parties;

- The annulment by the beneficiary in case the obligations are not respected by the operator;

- The bankruptcy of one of the parties.

- Unilateral, through a decision of the local council motivated by the interest of the local community in the implementation of the Project.

In the case of the annulment, the following can be proposed:

- The ending date of the old contract will be on the date on which the new contract with the new operator will begin it’s effects;

- The employees of the operator can be transferred to the new operator;

- The local council or the new operator will acquire the equipment found in the position of the operator and used for the sanitation services;

Taking all of the above into account, the IDA members has agreed that all the collection contracts for zones 1,2 and 8 will be tender at the beginning of the operational phase. Therefore, the current collection contracts will continue till the end of the implementation phases, and after that the LCs agreed to enter into the proposed contractual framework (a sole operator covering at least one collection area).

#### Patrimony

A distinction has to be made between public and private patrimony both being in the ownership of a public entity.

A public patrimony cannot be sold whereas a private patrimony can be sold and transferred to a new owner. In order to transfer a public patrimony to a new owner it has first to be altered into a private patrimony which the owner of the public patrimony is free to do.

#### Right of administration

In principle no transfer of land will take place between administrative territorial units as the owner of the land and the county council as beneficiary of the project. Instead the county council will receive the right of administration for the land, the facilities as landfill and transfer stations will be constructed on according to legal provisions regarding the public ownership (Law no 213/1998), granted by a decision of the local council of the owner municipality, which can be accompanied also by a further agreement between the county and the owner municipality stipulating the purpose and the conditions of the exercise of such right of administration Through this right of administration the county council will be set in a position to fulfill its responsibilities in respect to the implementation of the facilities.

The administrative orders which assure the transfer of the right of administration to the Project are the following:

Pitesti

- WMC: LCO nr. 390/18.10.2006 – 33, 67 ha;

- WMC – Cell 2 extension – LCO Pitesti nr 167-16.05.2007; CCO Arges nr. 60 -24.05.2007, and LCO 233 - 17.07.2007

- Green points LCO nr.202/20.06.2006 – 500 mp for two green points;

Campulung:

- Transfer station: LCO nr. 145/11.10. 2007 – 7640,5 m3;

- Old landfill: LCO nr. 44/31.05.2005 m3;

- Green point: LCO nr. 58/27.04.2006 – 250 m3;

Mioveni:

- Green point: LCO nr.24/16.03.2006 – 350 m3;

Curtea de Arges:

- Transfer station: LCO nr. 129/27.10.2009 – 53.538 m3;

- Green point: LCO nr. 129/27.10.2009 – 306 m3;

Costesti:

- Transfer station: LCO nr. 38/29.12.2004 – 5000 m3;

#### Conclusions and recommendations

In conclusion, it is recommended that service delivery for all required waste management services will be undertaken through PPP framework, which means Services, Management or Lease type of Contracts. The local authorities will deliver waste management services through “delegated management” contracts. If the delivery of waste management services will be performed using facilities and/or equipment owned by the public authorities, management delegation contracts will take the form of lease contracts that will specify (among other things) performance criteria and maintenance schedule(s) that the contractor will be responsible to maintain as a condition of payment and which will be monitored by the PIU together with the IDA Executive Committee members.

In summary, three contractual frameworks with the private operators will be established, which will lead to a number of maximum 7 operators for the whole system.

The transitional arrangements between Phase-1 and Phase-1 are not significant, since the operator of the WMC is the same for Cell-2 as it was for Cell-1, and the new collection operators will be selected without impairing in any way the functionality of the service in the other zones.

For the zones targeted by Phase-2, all IDA members decided that, after the finalisation of the Project, the current collection contracts will be annulled and the new collection contracts will be tender for a period of 8 years,. The WMC contract, which it is be tender in 2010 for a period of 20 years, will be amended, in order to include the subsequent services introduced by Phase-2.

All the bins and containers shall be made of an adequate material (injection moulded using high quality HDPE plastic or manufactured from high quality deep pressed sheet steel) with appropriate design to ensure stability and resistance to mechanical stresses, UV and heat resistant, for maximum durability, shaped for easy use and with required accessories to ensure a safe and easy movement. All the bins and containers shall be design in accordance with European Norm EN 840-2/5/6